## Slide 1: Chapter 10: Creating and Developing the Project Plan

## Slide 2: Overview
DNP project plan is a formal document
Successful project implementation
  Carefully considered plan
  Attention to detail
Points to consider in project creation and plan development

## Slide 3: Objectives
Create alternate strategies
Choose best solution
  Cost–benefit analysis
Understand components
Analyze components
Consider Institutional Review Board approval processes impact on the timeline

## Slide 4: Creation of Innovation
Phenomenon of interest has evolved
Literature review
General concept commitment that will evolve
New skill development

## Slide 5: Project Development Process Phases
Assessment
Diagnosis
Planning
Implementation
Evaluation

## Slide 6: Tools
SWOT analysis
Force field analysis
Community analysis
Needs assessment
Organizational data
Framing problem

## Slide 7: Tools – cont’d
Problem statement
Potential alternative solutions
Cost–benefit comparisons
Identify optimal solution
Plan for implementation
Metric/outcome development

## Slide 8: Tools – cont’d
Project plan in process
Metrics
Satisfaction
Clinical outcomes
Cost outcomes
Other measures

## Slide 9: DNP Project Plan
Environmental planning
  Identify the setting
  Collaborate with content expert
  Interface with committee and/or advisor
Proposal development

## Slide 10: DNP Project Plan – cont’d
Obtaining Institutional Review Board (IRB) approval
Submitting for grant support
Developing DNP project plan
Selecting items for project planning

## Slide 11: Identifying the Setting
Important early aspect in plan development
Where will this project be applied?
  Investigate options
  Secure a location
For project’s outside work environment, schedule extra time for the approval

## Slide 12: Plan Example
Table of Contents
Introduction
Executive Summary
Project Goals and Objectives
Scope
Project Administration
Project Management

## Slide 13: Plan Example – cont’d
7. Software and Hardware Requirements
8. Work Breakdown Structure
9. Quality Management
10. Project Initiation Plan
11. Training Plan
12. Procurement Plan
13. Appendices

## Slide 14: Collaborating with Content Experts
Collaboration is an important part of doctoral work
  Assists student growth
  Adds richness
Identify student’s areas of expertise
Identify where a content expert is needed

## Slide 15: Institutional Review Board (IRB)
Consideration given to human subject approval
Prior acceptance by the project team
Incomplete submissions slow progress
3 categories of review
  Exempt
  Expedited
  Full review

## Slide 16: Institutional Review Board (IRB) Approval
Avoid an incomplete or flawed submission
Be consistent in all documents
Provide all survey tools used
Be in contact with your IRB member
Consider audience
Prepare thorough application
Keep requirements in mind
Realistic time frame

## Slide 17: Grant Support
Provide financial assistance for project
Application process encourages clarity
Look for small grants in areas of specialty
Grants available for novice researchers or students

## Slide 18: Grant Writing
Tailor the grant
Showcase your expertise
Minimize reviewer’s work
Follow instructions exactly
Take advantage of resources for preparing and submitting
Contact agency’s program officer with questions
Tell an interesting story

## Slide 19: Implementation of DNP Project
Successful project variables
  Completing on time
  Completing within budget
  Achieving intended goals
  Achieving stakeholder satisfaction
  Project management and change management

## Slide 20: Implementation of DNP Project
Project structure
  Finalize project implementation details
Coordinate with organizations involved
Prepare infrastructure
Form team and implement training
  Forming, storming, norming, and performing